## Resource
Name | Role | Discipline | Working Hours (FT-20%) | Contract Type | Supervisor | Project | Project Manager
Onur Kavakli | Principal Engineer | Process / Technical | 40 | Employee | Jim Latto | P250001 ADOC | Tim
Maria Alonzo | Project Manager | PM | 40 | Employee | Jim Latto | P230195 OXY Oman | Dion
Jacobo Ramirez | Project Manager (In-Country) | PM | 40 | Employee | Jim Latto | P230073 Almansoori
Boris Welzen | Procurement Manager (Freelance) | Procurement | 40 | Employee | Jim Latto | P260002 Spare parts Zeeland
Rutger Reij | Mechanical Engineer | Mechanical | 40 | Employee | Jim Latto | P26001 TAQA
Anwar Hassan | Mechanical Engineer | Mechanical | 40 | Employee | Jim Latto | SARAT
Neville Cory | Process Engineer | Process | 40 | Employee | Onur Kavakli | CANCUN
Fatemeh Rashidashmagh | Process Engineer | Process | 40 | Employee | Onur Kavakli
William Garcia | Process Engineer | Process | 40 | Employee | Onur Kavakli
Ajitha Karuppiah | Draughtsperson | Drafting | 40 | Employee | Jim Latto

## Sheet3
|  |  |  | June |  | July |  | August |  | September |  | October |  | November |  | December
P250001 ADOC |  |  |  | 242.7827 | 2 | 87.329 | 0.7 | 141.3663 | 1.15 | 67.354 | 0.55 | 100.6457 | 0.8 | 100.6457 | 0.8 | 0 | 0
Maria Alonzo | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Jacobo Ramirez | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Boris Welzen | 133.1667 |  |  | 39.95 | 30% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Rutger Reij | 103.7283 |  |  | 82.9827 | 80% | 20.7457 | 20% | 41.4913 | 40% | 20.7457 | 20% | 20.7457 | 20% | 20.7457 | 20% | 0 | 0%
Fatemeh Rashidashmagh | 133.1667 |  |  | 13.3167 | 10% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
William Garcia | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Ajitha Karuppiah | 133.1667 |  |  | 13.3167 | 10% | 13.3167 | 10% | 6.6583 | 5% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Anwar Hassan | 133.1667 |  |  | 39.95 | 30% | 13.3167 | 10% | 39.95 | 30% | 19.975 | 15% | 26.6333 | 20% | 26.6333 | 20% | 0 | 0%
Neville Cory | 133.1667 |  |  | 39.95 | 30% | 26.6333 | 20% | 26.6333 | 20% | 13.3167 | 10% | 26.6333 | 20% | 26.6333 | 20% | 0 | 0%
Onur Kavakli | 133.1667 |  |  | 13.3167 | 10% | 13.3167 | 10% | 26.6333 | 20% | 13.3167 | 10% | 26.6333 | 20% | 26.6333 | 20% | 0 | 0%
P230195 OXY Oman |  |  |  | 80.6707 | 0.65 | 83.6145 | 0.65 | 100.6457 | 0.8 | 18.5031 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
Maria Alonzo | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Jacobo Ramirez | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Boris Welzen | 133.1667 |  |  | 6.6583 | 5% | 6.6583 | 5% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Rutger Reij | 103.7283 |  |  | 20.7457 | 20% | 10.3728 | 10% | 20.7457 | 20% | 5.1864 | 5% | 0 | 0% | 0 | 0% | 0 | 0%
Fatemeh Rashidashmagh | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
William Garcia | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Ajitha Karuppiah | 133.1667 |  |  | 13.3167 | 10% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Anwar Hassan | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Neville Cory | 133.1667 |  |  | 13.3167 | 10% | 39.95 | 30% | 39.95 | 30% | 6.6583 | 5% | 0 | 0% | 0 | 0% | 0 | 0%
Onur Kavakli | 133.1667 |  |  | 26.6333 | 20% | 26.6333 | 20% | 39.95 | 30% | 6.6583 | 5% | 0 | 0% | 0 | 0% | 0 | 0%
P230073 Almansoori |  |  |  | 106.5333 | 0.8 | 46.6083 | 0.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maria Alonzo | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Jacobo Ramirez | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Boris Welzen | 133.1667 |  |  | 6.6583 | 5% | 6.6583 | 5% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Rutger Reij | 103.7283 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Fatemeh Rashidashmagh | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
William Garcia | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Ajitha Karuppiah | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Anwar Hassan | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Neville Cory | 133.1667 |  |  | 33.2917 | 25% | 6.6583 | 5% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Onur Kavakli | 133.1667 |  |  | 66.5833 | 50% | 33.2917 | 25% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
P260002 Spare parts Zeeland |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maria Alonzo | 133.1667 |  |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Jacobo Ramirez | 133.1667 |  |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Boris Welzen | 133.1667 |  |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Rutger Reij | 103.7283 |  |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Fatemeh Rashidashmagh | 133.1667 |  |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
William Garcia | 133.1667 |  |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Ajitha Karuppiah | 133.1667 |  |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Anwar Hassan | 133.1667 |  |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Neville Cory | 133.1667 |  |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Onur Kavakli | 133.1667 |  |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
P260001 TAQA |  |  |  | 426.1333 | 3.2 | 439.45 | 3.3 | 359.55 | 2.7 | 159.8 | 1.2 | 113.1917 | 0.85 | 99.875 | 0.75 | 126.5083 | 0.95
Maria Alonzo | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Jacobo Ramirez | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Boris Welzen | 133.1667 |  |  | 53.2667 | 40% | 66.5833 | 50% | 66.5833 | 50% | 39.95 | 30% | 39.95 | 30% | 39.95 | 30% | 39.95 | 30%
Rutger Reij | 103.7283 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Fatemeh Rashidashmagh | 133.1667 |  |  | 66.5833 | 50% | 66.5833 | 50% | 66.5833 | 50% | 26.6333 | 20% | 13.3167 | 10% | 6.6583 | 5% | 19.975 | 15%
William Garcia | 133.1667 |  |  | 66.5833 | 50% | 66.5833 | 50% | 66.5833 | 50% | 26.6333 | 20% | 13.3167 | 10% | 6.6583 | 5% | 19.975 | 15%
Ajitha Karuppiah | 133.1667 |  |  | 93.2167 | 70% | 93.2167 | 70% | 39.95 | 30% | 13.3167 | 10% | 0 | 0% | 0 | 0% | 0 | 0%
Anwar Hassan | 133.1667 |  |  | 93.2167 | 70% | 93.2167 | 70% | 66.5833 | 50% | 26.6333 | 20% | 19.975 | 15% | 19.975 | 15% | 19.975 | 15%
Neville Cory | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Onur Kavakli | 133.1667 |  |  | 53.2667 | 40% | 53.2667 | 40% | 53.2667 | 40% | 26.6333 | 20% | 26.6333 | 20% | 26.6333 | 20% | 26.6333 | 20%
P250002 Cancun CISEC |  |  |  | 346.2333 | 2.6 | 359.55 | 2.7 | 372.8667 | 2.8 | 386.1833 | 2.9 | 386.1833 | 2.9 | 386.1833 | 2.9 | 386.1833 | 2.9
Maria Alonzo | 133.1667 |  |  | 79.9 | 60% | 79.9 | 60% | 79.9 | 60% | 79.9 | 60% | 79.9 | 60% | 79.9 | 60% | 79.9 | 60%
Jacobo Ramirez | 133.1667 |  |  | 133.1667 | 100% | 133.1667 | 100% | 133.1667 | 100% | 133.1667 | 100% | 133.1667 | 100% | 133.1667 | 100% | 133.1667 | 100%
Boris Welzen | 133.1667 |  |  | 13.3167 | 10% | 26.6333 | 20% | 39.95 | 30% | 53.2667 | 40% | 53.2667 | 40% | 53.2667 | 40% | 53.2667 | 40%
Rutger Reij | 103.7283 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Fatemeh Rashidashmagh | 133.1667 |  |  | 39.95 | 30% | 39.95 | 30% | 39.95 | 30% | 39.95 | 30% | 39.95 | 30% | 39.95 | 30% | 39.95 | 30%
William Garcia | 133.1667 |  |  | 39.95 | 30% | 39.95 | 30% | 39.95 | 30% | 39.95 | 30% | 39.95 | 30% | 39.95 | 30% | 39.95 | 30%
Ajitha Karuppiah | 133.1667 |  |  | 13.3167 | 10% | 13.3167 | 10% | 13.3167 | 10% | 13.3167 | 10% | 13.3167 | 10% | 13.3167 | 10% | 13.3167 | 10%
Anwar Hassan | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Neville Cory | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Onur Kavakli | 133.1667 |  |  | 26.6333 | 20% | 26.6333 | 20% | 26.6333 | 20% | 26.6333 | 20% | 26.6333 | 20% | 26.6333 | 20% | 26.6333 | 20%
QDG2600002 SARAT |  |  |  | 159.8 | 1.2 | 186.4333 | 1.4 | 159.8 | 1.2 | 186.4333 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0
Maria Alonzo | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 0
Jacobo Ramirez | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 0
Boris Welzen | 133.1667 |  |  | 26.6333 | 20% | 26.6333 | 20% | 26.6333 | 20% | 26.6333 | 20% | 0 |  | 0 |  | 0
Rutger Reij | 103.7283 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 0
Fatemeh Rashidashmagh | 133.1667 |  |  | 39.95 | 30% | 53.2667 | 40% | 53.2667 | 40% | 53.2667 | 40% | 0 |  | 0 |  | 0
William Garcia | 133.1667 |  |  | 39.95 | 30% | 53.2667 | 40% | 53.2667 | 40% | 53.2667 | 40% | 0 |  | 0 |  | 0
Ajitha Karuppiah | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 0
Anwar Hassan | 133.1667 |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 0
Neville Cory | 133.1667 |  |  | 26.6333 | 20% | 26.6333 | 20% | 13.3167 | 10% | 26.6333 | 20% | 0 |  | 0 |  | 0
Onur Kavakli | 133.1667 |  |  | 26.6333 | 20% | 26.6333 | 20% | 13.3167 | 10% | 26.6333 | 20% | 0 |  | 0 |  | 0
|  | 5 days | 4 days
Contracted hours: 40 h/week × 52 weeks | 2080 | 173.3333 | 138.7
Leave allowance: 25 days × 8 h | 200 | 16.6667 | 16.6667
Admin/management allowance: 15% | 282 | 23.5 | 18.305
Project/productive capacity | 1598 | 133.1667 | 103.7283
Employee |  | Available Hours | June | Remaining % | July | Remaining % | August | Remaining % | September | Remaining % | October | Remaining % | November | Remaining % | December | Remaining %
Maria Alonzo | LATAM PM | 133.1667 | 79.9 | 40% | 79.9 | 40% | 79.9 | 40% | 79.9 | 40% | 79.9 | 40% | 79.9 | 40% | 79.9 | 40%
Jacobo Ramirez | LATAM PM | 133.1667 | 133.1667 | 0% | 133.1667 | 0% | 133.1667 | 0% | 133.1667 | 0% | 133.1667 | 0% | 133.1667 | 0% | 133.1667 | 0%
Boris Welzen | Procurement | 133.1667 | 146.4833 | -10% | 133.1667 | 0% | 133.1667 | 0% | 119.85 | 10% | 93.2167 | 30% | 93.2167 | 30% | 93.2167 | 30%
Rutger Reij | Mech. Eng. | 103.7283 | 103.7283 | 0% | 31.1185 | 70% | 62.237 | 40% | 25.9321 | 75% | 20.7457 | 80% | 20.7457 | 80% | 0 | 100%
Fatemeh Rashidashmagh | Proc. Eng. | 133.1667 | 159.8 | -20% | 159.8 | -20% | 159.8 | -20% | 119.85 | 10% | 53.2667 | 60% | 46.6083 | 65% | 59.925 | 55%
William Garcia | Proc. Eng. | 133.1667 | 146.4833 | -10% | 159.8 | -20% | 159.8 | -20% | 119.85 | 10% | 53.2667 | 60% | 46.6083 | 65% | 59.925 | 55%
Ajitha Karuppiah | Mech. Eng. | 133.1667 | 133.1667 | 0% | 119.85 | 10% | 59.925 | 55% | 26.6333 | 80% | 13.3167 | 90% | 13.3167 | 90% | 13.3167 | 90%
Anwar Hassan | Mech. Eng. | 133.1667 | 133.1667 | 0% | 106.5333 | 20% | 106.5333 | 20% | 46.6083 | 65% | 46.6083 | 65% | 46.6083 | 65% | 19.975 | 85%
Neville Cory | Proc. Eng. | 133.1667 | 113.1917 | 15% | 99.875 | 25% | 79.9 | 40% | 46.6083 | 65% | 26.6333 | 80% | 26.6333 | 80% | 0 | 100%
Onur Kavakli | Proc. Eng. | 133.1667 | 213.0667 | -60% | 179.775 | -35% | 159.8 | -20% | 99.875 | 25% | 79.9 | 40% | 79.9 | 40% | 53.2667 | 60%
Total
Consumed |  |  | 1362.1533 |  | 1202.9852 |  | 1134.2287 |  | 818.2737 |  | 600.0207 |  | 586.704 |  | 512.6917
Capacity |  |  | 1302.2283 |  | 1302.2283 |  | 1302.2283 |  | 1302.2283 |  | 1302.2283 |  | 1302.2283 |  | 1302.2283
LATAM PM | Consumed |  | 213.0667 |  | 213.0667 |  | 213.0667 |  | 213.0667 |  | 213.0667 |  | 213.0667 |  | 213.0667
| Capacity |  | 266.3333 |  | 266.3333 |  | 133.1667 |  | 133.1667 |  | 133.1667 |  | 133.1667 |  | 133.1667
Procurement | Consumed |  | 146.4833 |  | 133.1667 |  | 133.1667 |  | 119.85 |  | 93.2167 |  | 93.2167 |  | 93.2167
| Capacity |  | 133.1667 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Mech. Eng. | Consumed |  | 370.0617 |  | 257.5018 |  | 228.6953 |  | 99.1737 |  | 80.6707 |  | 80.6707 |  | 33.2917
| Capacity |  | 370.0617 |  | 370.0617 |  | 370.0617 |  | 370.0617 |  | 370.0617 |  | 370.0617 |  | 370.0617
Proc. Eng. | Consumed |  | 632.5417 |  | 599.25 |  | 559.3 |  | 386.1833 |  | 213.0667 |  | 199.75 |  | 173.1167
| Capacity |  | 532.6667 |  | 532.6667 |  | 532.6667 |  | 532.6667 |  | 532.6667 |  | 532.6667 |  | 532.6667
Should we add Dion, Maarten and me as a recource as well?
Because we do have LATAM PM's in here

## PM Request
Project | PM | Status | Discipline | Jun/26 | Jul/26 | Aug/26 | Sept/26 | Oct/26 | Nov/26 | Dec/26 | Confidence | Notes / assumptions