## Instructions
Capacity Planner – Expected Loading Input
There is one tab per person below (see sheet tabs at the bottom).
On your tab, enter your expected % allocation to each project for each of the next 6 months.
Use whole percentages, e.g. 50 for 50%. Leave a cell blank if you expect 0% on that project that month.
The "Total" row at the bottom of your tab adds up your entries — it will turn red if a month exceeds 100%.
If you are expecting to work on a project not listed, use the "Other / New Opportunity" row and add detail in the Notes column.
Please fill in your own tab only. Do not edit other tabs or the project/month headers.
Projects covered:
Project | Client / Status
Cancun CISEC (P250002) | CISEC — Active
TAQA (P260001) | TAQA — Active
ADOC (P250001) | ADOC — Active
OXY Oman (P230195) | OXY — Active (wind-down)
Almansoori (P230073) | Almansoori — Active (near close-out)
Spare Parts Zeeland (P260002) | Zeeland — On Hold
SARAT (QDG2600002) | SARAT — Pipeline opportunity
Sales and Quotations Effort (SALES) | Internal — Ongoing internal

## Onur Kavakli
Expected Loading — Onur Kavakli (Process Engineering / Principal Engineer)
Enter expected % allocation per project per month. Totals per month should not exceed 100%.
Project | Client | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Notes
Cancun CISEC | CISEC
TAQA | TAQA | 20 | 20 | 10 | 10 | 5 | 0 | Planned to finish by December for delivery, however more commissioning activities and support may be required in JAN.
ADOC | ADOC | 10 | 10 | 10 | 10 | 10 | 10
OXY Oman | OXY | 0 | 0 | 10 | 10 | 0 | 0 | Oxy expected to pick back up in October for commissioning
Almansoori | Almansoori | 20 | 20 | 20 | 20 | 20 | 20 | Unknown when the package problems will subside
Spare Parts Zeeland | Zeeland
SARAT | SARAT
Sales and Quotations Effort | Internal | 50 | 50 | 50 | 50 | 65 | 65 | ✌ Sales effort is limited by engineering on actual projects, however since we don't have anything firmly lined up after TAQA/ADOC, the sales effort will increase by DEC.
Other / New Opportunity (specify in Notes)
Total |  | 100 | 100 | 100 | 100 | 100 | 95

## Maria Alonzo
Expected Loading — Maria Alonzo (Project Management / Project Manager)
Enter expected % allocation per project per month. Totals per month should not exceed 100%.
Project | Client | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Notes
Cancun CISEC | CISEC
TAQA | TAQA
ADOC | ADOC
OXY Oman | OXY
Almansoori | Almansoori
Spare Parts Zeeland | Zeeland
SARAT | SARAT
Sales and Quotations Effort | Internal
Other / New Opportunity (specify in Notes)
Total |  | 0 | 0 | 0 | 0 | 0 | 0

## Jacobo Ramirez
Expected Loading — Jacobo Ramirez (Project Management / Project Manager (In-Country))
Enter expected % allocation per project per month. Totals per month should not exceed 100%.
Project | Client | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Notes
Cancun CISEC | CISEC | 100 | 100 | 100 | 100 | 100 | 100
TAQA | TAQA
ADOC | ADOC
OXY Oman | OXY
Almansoori | Almansoori
Spare Parts Zeeland | Zeeland
SARAT | SARAT
Sales and Quotations Effort | Internal
Other / New Opportunity (specify in Notes)
Total |  | 100 | 100 | 100 | 100 | 100 | 100

## Boris Welzen
Expected Loading — Boris Welzen (Procurement / Procurement Manager)
Enter expected % allocation per project per month. Totals per month should not exceed 100%.
Project | Client | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Notes
Cancun CISEC | CISEC
TAQA | TAQA
ADOC | ADOC
OXY Oman | OXY
Almansoori | Almansoori
Spare Parts Zeeland | Zeeland
SARAT | SARAT
Sales and Quotations Effort | Internal
Other / New Opportunity (specify in Notes)
Total |  | 0 | 0 | 0 | 0 | 0 | 0

## Rutger Reij
Expected Loading — Rutger Reij (Mechanical Engineering / Mechanical Engineer)
Enter expected % allocation per project per month. Totals per month should not exceed 100%.
Project | Client | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Notes
Cancun CISEC | CISEC
TAQA | TAQA |  | 10 | 10 | 10 | 10
ADOC | ADOC |  | 55 | 40 | 40 | 40
OXY Oman | OXY |  | 30 | 40 | 40 | 40
Almansoori | Almansoori |  | 5 | 5 | 5 | 5
Spare Parts Zeeland | Zeeland
SARAT | SARAT
Sales and Quotations Effort | Internal
Other / New Opportunity (specify in Notes) |  |  |  | 5 | 5 | 5 |  | R&D, future projects, mechanical library
Total |  | 0 | 100 | 100 | 100 | 100 | 0

## Anwar Hassan
Expected Loading — Anwar Hassan (Mechanical Engineering / Mechanical Engineer)
Enter expected % allocation per project per month. Totals per month should not exceed 100%.
Project | Client | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Notes
Cancun CISEC | CISEC
TAQA | TAQA
ADOC | ADOC
OXY Oman | OXY
Almansoori | Almansoori
Spare Parts Zeeland | Zeeland
SARAT | SARAT
Sales and Quotations Effort | Internal
Other / New Opportunity (specify in Notes)
Total |  | 0 | 0 | 0 | 0 | 0 | 0

## Ajitha Karuppiah
Expected Loading — Ajitha Karuppiah (Drafting / Draughtsperson)
Enter expected % allocation per project per month. Totals per month should not exceed 100%.
Project | Client | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Notes
Cancun CISEC | CISEC
TAQA | TAQA | 30 | 35 | 40 | 45 | 50
ADOC | ADOC | 20 | 20 | 30 | 30 | 25
OXY Oman | OXY | 30 | 20 | 15 | 15 | 15
Almansoori | Almansoori
Spare Parts Zeeland | Zeeland | 10 | 15 | 5
SARAT | SARAT
Sales and Quotations Effort | Internal
Other / New Opportunity (specify in Notes) |  | 10 | 10 | 10 | 10 | 10 |  | For Quotation
Total |  | 100 | 100 | 100 | 100 | 100 | 0

## Neville Cory
Expected Loading — Neville Cory (Process Engineering / Process Engineer)
Enter expected % allocation per project per month. Totals per month should not exceed 100%.
Project | Client | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Notes
Cancun CISEC | CISEC
TAQA | TAQA | 9 | 10 | 5 | 5
ADOC | ADOC | 90 | 45 | 45 | 25 | 10 | 10
OXY Oman | OXY |  | 45 | 50 | 70 | 90 | 90
Almansoori | Almansoori
Spare Parts Zeeland | Zeeland | 1
SARAT | SARAT
Sales and Quotations Effort | Internal
Other / New Opportunity (specify in Notes)
Total |  | 100 | 100 | 100 | 100 | 100 | 100

## Fatemeh Rashidashmagh
Expected Loading — Fatemeh Rashidashmagh (Process Engineering / Process Engineer)
Enter expected % allocation per project per month. Totals per month should not exceed 100%.
Project | Client | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Notes
Cancun CISEC | CISEC | 3.75
TAQA | TAQA | 81.56 | 40
ADOC | ADOC | 3.44
OXY Oman | OXY
Almansoori | Almansoori
Spare Parts Zeeland | Zeeland
SARAT | SARAT
Sales and Quotations Effort | Internal | 10 | 10
Other / New Opportunity (specify in Notes) |  | 1.25 | 50 |  |  |  |  | Holiday
Total |  | 100 | 100 | 0 | 0 | 0 | 0

## William Garcia
Expected Loading — William Garcia (Process Engineering / Process Engineer)
Enter expected % allocation per project per month. Totals per month should not exceed 100%.
Project | Client | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Notes
Cancun CISEC | CISEC |  | 25
TAQA | TAQA |  | 50
ADOC | ADOC
OXY Oman | OXY
Almansoori | Almansoori
Spare Parts Zeeland | Zeeland
SARAT | SARAT
Sales and Quotations Effort | Internal |  | 10
Other / New Opportunity (specify in Notes) |  |  | 15 |  |  |  |  | Working in new documentation such as templates for SOPs, HAZID report, workshops, etc
Total |  | 0 | 100 | 0 | 0 | 0 | 0